## Main
Sl. No. | Module | Task | Owner | Status | Updation | Deadline/Remarks | Updates as on 20th | actions on 20th | UPDATES 22/07/2026 | 31/07/2026 | 2026-03-08 |  | Update on 6th Aug
1 | DocuWare | Confirm deadline for Advance Payment through (EBS) | Riyas / EBS Team | Pending | Account team is testing - need to reply back the finding | This week | daley will update, (single customer when adding liek 3 or more adivec one gets missed, avance payemnt request process is done the advance payment price shouldnt abe abel to chnage, now they can do it through note that optionshould be blocked. update | follow up with daley today | today final , live connected, to be tested in live, it will be done by tomrrow | docuware license count is low, so need more users, currently they are using it using existing users, quotation is given for 15 users bundle, navab to reply on what to do going forward. | docuware noufal sir will contact | licence purchse negitiiattion, updated propaslw will be snet, need to remind sir
2 | DocuWare | Complete Abu Dhabi workflow & validation | DocuWare Team | In Progress |  |  | its already implemeted they are not using it. | ask sir. | ask sir | to be informed to management | audit, sir
3 | DocuWare | Send KSA completion email & confirm requirements | IT Team | Pending |  |  | apart from an error , everything else is completed and rolledout. need to follow up on the error fixing | follow up ksa team and udpate | everything is fixed rolled out |  | done, testing
4 | DocuWare | Obtain Qatar implementation schedule | DocuWare Team | Pending |  |  | the process is started, qatar staff ajnas needs to provide, requiremnt of the documenst to nbe added in docuware | follow up with qatar team |  | need licence if we need to go forward | need the license point 1 | after user purcase | after user purcase
5 | DocuWare | Approval through form - need confirmation from team - need to sent email to get the confirmation | Riyas | Pending | check with team what requiremnt this is riyas |  |  |  | ask around between each whose requirement this is. | abudabi, dubai its not being used, need to push to mangemnet everything is imlemented and users are trained | cashier form and pay,meny advice form both are impnmented and rolled out | advice oayment , ,abudabi qatar riyas, everything else abhi
6 | Olive HR | Share SSH access for KSA | Riyas / Abhimanue | done |  | Have application access - need ssh access to the system | Access has been shared - the team needs a sql database - database change request sent to the team |  | it is viable, contact janeesh and given traing for shift /timetasble configuration in the system, ksa team, oman team qatar team, ask janeesh whom to train for each region | databse change has beeen completed, server connection is to be confirmed by olive, follow up Abhimanue Rajesh | follow up done today | meeting oman and qatar , test by abhi ksa and qatar ana oman,a nd team should mail. saudi shoud be tested and confimred and mail should ne sent | completed , test it Abhimanue Rajesh, qatar, oman, 8/08/26 - will sent a mail to the team to get confirmation on all the features are updated and live
7 | Olive HR | Update Nabeel issue | Olive Team | need confirmation from nabeel havent gotten yet |  |  | need to follow up with bininsha |  | reminder mail has been send to binsha 22/07/26 12pm, no reply from bonsha, sir escalation | done,confirm with nabeel Abhimanue Rajesh | follow up mail sent - Attendanace system timing error |  | done
8 | Olive HR | Share updated activity sheet | Olive Team, Abhimanue Rajesh Russel Ravindran | Pending | will mail back in half hour - 16th 07 | Email subject - Request to Update Deadlines for UAQ Action Items |  |  | activity sheet to be updated by olive team
9 | Olive HR | Confirm latest India HR Excel - Employee details need confirmation from Indian HR | HR/ Abhimanue | done |  | Abhimanue Will get an update from the indian HR | Confirmation waiting from Kochi HR |  | get conformation form kochi hr akhil |  | hr mailed new issues on 3rd aug - sent to the olive team to get the solutions - Confirmation on Olive, Attendance System & EBS Integration -Email |  | calender year to be set to jan -dec, for all leaves- Olive to update on this , 12/08/26
10 | EBS | purging , maintenance | Riyas | Pending |  | 1–2 PM maintenance | in progress, |  | they ll do it today too, dxb will be done today purging, tomorrow abhidabi, after that shrinking will take time after that | dxb shrinking is done. abudabi still pending needs 2 more session 2 days | 2 more days pending , | attendence olive and ebs should be integrated , it is done in uae it should be adapted to uae, abhimanue should, | 2026-07-08
11 | EBS | Clarify billing separation benefits - | Riyas / EBS Team | Pending |  | riyas to mail this to them and get an update | ask to daley what are the beifits of splitting the billing database |  |  | not now after meeting | after meeting irl(ai) |  | during ai meeting
12 | EBS | Schedule AI Demo | EBS Team / Russell | Planned |  | Next week - meeting to be arraigned - jauhar to check |  | shedue the meeting today russel | mail sent to jauhar waiting for the schedule | cleaning the databases. Once this exercise is complete, we plan to schedule a meeting at your office for a review." is what jauhar said | ASK DATE TODAY | next week wndnedsday 12 | next week wndnedsday 12
13 | E-Invoicing | Meeting with Finance, EBS & ASP | Finance / EBS / ASP | Pending | rahim will contact us after mubashir arrives , we'll have a meeting with asp after. | next week | ask rahim what the update is |  | monday mubashir will come update with rahim ikka | check with rahim | ASK RAHIM DATE TODAY | 10 | next week wndnedsday 15
14 | POS | Compare shortlisted solutions | IT Team | In Progress |  | This week | in progress, check with sir , whether to xonfim it or not | shortlisted selected a team, revised quaotatis asked they will provide it | waiting fro the revised quotation | requirement should be provided with written proof by mail from the finance department | follow up mail is sent , requirment should be provided |  | requirement to be shared from finance
15 | CRM | Complete integration & testing | IT Team | In Progress |  | Work in progress - need to follow up and speed up | testing, its going fine from both ends. | they are testing the end points for far too long | currently with crm team to rpovide the live endpoints | The schedule and frequency at which each report should be sent to the CRM.reply to daley, ask her the frequency in which each report is being updated in ebs, accordingly we ll provide the schedule and frequency in whci ggh the report should be sent to crm stage database, or ask daley , if no reply ask accounts team | follow up with daley | complete the integration this week | 2026-08-08
16 | Agentic AI | Review proposals | IT Team | In Progress |  | Neo Soft - and other software | neuralence.ai follow up they havent contacted after the details about integration and requiremnt was provided, neosoft quoation shoudl be negotiated, |  |  |  |  | nda shoudl be signed friday, proposal should be taken and arrange communicate abhimanue | follow up approlabs, digital difinity , neosoft
17 | Staffing | Prepare JD for Application Support Engineer | Russel | Pending | done, need to send to HR |  | sent mail to hr.talent@thedeepseafood.com, MPR | Must provide JD |  |  |  |  | done
18 | Royal Future | Start development after UI approval | Designing Team | Pending |  | Waiting for designing to be completed |  |  |  | amar should coordinate | internal meeting with the desining team toady - 03rd Aug - need to sent the design review to the development team |  | Internal confirmation need before the development starts - 06th will get the internal confirmation
19 | Import Purchase EBS | Get Ibrahim confirmation & send completion email | Abhimanue | Pending |  |  | Implementation of Approval Levels for Imports - need to confirm with ibrahim kutty on this | Abhimanue Rajesh should mail to ibrahim ikka to get confirmation |  | RE: Ticket Received - Case:11097 - Functional Requirement: Dedicated PO Import Screen and Hierarchy, Implementation of Approval Levels for Imports, follow up mail ,requiring confimration from the TDSC team. | follow up mail sent today | 06/08 meeting interanl | ask sir, RE: Ticket Received - Case:12163 - Enhancement Request for IRE Document Process mail to tdsc team to follow up on the quoattion
20 | Internal Apps | Review ongoing developments | Abhimanue / Russell | Ongoing |  |  |  | s |  |  | need testing |  | Need testing and we need to use this
21 | Visitors form | factory UAQ | Russel | Ongoing | Roll out complete, UAT testing on going | monday |  |  |  | done | done | done
22 | Visitors form | Gourmex Abalone | Russel | Ongoing | Configuration and training to be done, | next week |  |  |  | done, training given, config to be done | done, training given, config to be done | done, conf, ask them to come shj 09
23 | Visitors form | Oceano Kitchen | Russel | Ongoing | training done, configuration to be done | next week |  |  |  | done, training given, config to be done | done, training given, config to be done | done, conf 09
24 | Seafsoft | training , implemenattion go live deadline UAQ | Russel | Pending | training done, implementation done, testing ongoing, fixing bugs | Today |  |  |  | Ebs training and implementation done | Ebs training and implementation done
25 | Seafsoft | api integration ebs, | Russel | Pending | api documentation shared with |  |  |  |  | integration meeting to be done with the tdsc team | integration meeting to be done with the tdsc team | meeting internal 05 | morning 10
26 | Seafsoft | abalone gourmex | Russel | Pending | [5 empty] | quotation recieved in review, ceo approval is done, but only after Uaq api integration | quotation recieved in review, ceo approval is done, but only after Uaq api integration | quotation recieved in review, ceo approval is done, but only after Uaq api integration
27 | Seafsoft | oceano kitchen | Russel | Pending | [5 empty] | quotation recieved in review, ceo approval is done, but only after Uaq api integration | quotation recieved in review, ceo approval is done, but only after Uaq api integration | quotation recieved in review, ceo approval is done, but only after Uaq api integration
28 | Sales Automation | Start implementation | Russel | Planned |  | Next week |  |  |  |  | pending screens to be configured | pending screen to be developed
29 | HR Recruitment | Check usage & form requirement - Sent an email to the team to check if they are using and if anything else is needed | Russel | Pending | [5 empty] | ask hr team | forms to be automated to be asked to hr, please provide us with the forms and other documenst you would like to make part of the recruitement module provided | the mail has been sent on 3rda ug | Reminder sent to the hr team on 5th Aug - no update yet
30 | logistics, import team | form to be provided back to the vendor team | Russel | pending | didnt fill the form | today | [5 empty] | data safety issue cannot do it
31 | accounts reconciliation(Farhan ikka CFO) | Accounts reconciliation software | Russel | pending | Need to get back from farhan to give master data | next week |  |  |  |  | farhan to provide the master data
32 | Task management application pwa | task management application pwa | Abhimanue / Russell | pending | scrum, development | next week |  |  |  | meeting arrange | meeting at 10 | friday , monday meeting 10 th engineering team meeting , req gathethering 06/08
36 | AWS EBS integration | Billing Team | Russel /Riyas | Ongoing | EDI , SPI API integration need support from | next week |  |  |  | ozhvak
37 | crm feedback form |  | Riyas | [6 empty] | close, training session | closed
| POS ERP | Integration Requirements The integration should provide the following reports and summaries: Cash Sales Display the total cash sales at the end of each day (daily summary). Credit Sales (Customer-wise) Display total credit sales for each customer. Do not show only the overall credit sales total. If a customer (e.g., ABC Customer) has multiple invoices (e.g., 10 invoices), there is no need to list each invoice separately. Show only the total credit sales amount for that customer. Cash Purchases Display the total cash purchases on a daily basis. Credit Purchases (Supplier-wise) Display total credit purchases for each supplier. No invoice-level breakdown is required unless specifically requested. Customer Sales Summary Provide a customer-wise sales summary showing the total sales amount for each customer. Supplier Purchase Summary Provide a supplier-wise purchase summary showing the total purchase amount for each supplier. | [7 empty] | requirement should be provided with written proof by mail from the finance department
| centralised salary processing | centralise the salary processing for the entire group | russel | ongoing | Olive |  |  |  |  | Meeting with olive is done , the centralised processing can be done, each region need to be processed seperately. can be done by a single user wth sahred previlages or a team processing seperatly at the back office
| ot feature | division wise ot , copy previous day copy, 1-2 people just edit.